## Formato de PT 2008-2
[5 empty] | 1.5 | [22 empty] | PTFO1
PLAN DE TRABAJO ANUAL
Campus: Sistema CETYS Universidad |  |  | Dirección: CENTRO DE DESARROLLO DE EMPRENDEDORES | [19 empty] | Depto: | [6 empty] | Coordinación:
Elaboró: Dra Helia Cantellano G. |  |  | Año: 2008 | [19 empty] | Dirección:
Nivel estratégico
| Activities | Impact on objective | Responsible | Resources | Jul. |  |  |  | Aug. |  |  |  | Sept. |  |  |  | Oct. |  |  |  | Nov. |  |  |  | Dec. |  |  |  | Expected Outcome (Goal) | Comments | Importance | Achieved Outcome (from goal) | Assessment
| (actions, projects) |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | WASC Project To define the basis to consolidate CDE as the center that generates research linked to Majors and graduate students. To generate evidence. | 7 | Dr. Cantellano | [25 empty] | 100% | Research: mortality causes, entrepreneurs percentage in Cetys, documentation of success cases and book in process. | 8 | 80% | 6.4
2 | To foster entrepreneurial culture following the preincubation model of the Entrepreneurial Development Center in highschool and bachelor students. | 8,9 | Dr. Cantellano, Lic. Ernesto Romero, Lic. Gina Villalba, Lic. Erick Macip, Lic. Caridad Medina | [25 empty] | 100% | All CETYS students RECEIVE THIS INFORMATION | 7 | 100% | 7
3 | Organization of Asian Forum | 9,11 | Dr. Cantellano, MBA Paulina Vargas | [25 empty] | 100% | Successfuly carried out | 6 | 100% | 6
4 | To establish the Center as an Academic differentiation To participate in the curricular reform of 2009 academic programs to insert the entrepreneurial focus (corresponding subjects will be designed in bachelor programs) | 8,11 | Dr. Cantellano | [25 empty] | 100% | Proper spaces are defined in the new programs and the programs are ellaborated. | 7 | 100% | 7
5 | Consolidation of the funding to support new entrepreneurs through companies' donations. | 12 | Dr. Cantellano, MFC Lisette Salgado | [25 empty] | 40000 | Donation and funding candidates are kept | 7 | 100% | 7
6 | To start a positioning campaign towards the exterior of the entrepreneurial focus of CETYS students | 11 | All | [25 empty] | 100% | Asian Forum, Expos, Academic Promotion in schools and Entrepreneur Week, ENDEAVOR week | 5 | 100% | 5
40
Tactic Level
| Activities | Impact on objective | Responsible | Resources | Jul. 1: Jul.; Aug. 1: Aug.; Sept. 1: Sep.; Oct. 1: Oct.; Nov. 1: Nov.; Dec. 1: Dec. | Expected Outcome (Goal) | Comments | Importance | Achieved Outcome (from goal) | Assessment
| (actions, projects) |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | To coordinate the Center's general operation | 8 | Dr. Cantellano, MBA Paulina Vargas, MFC Lisette Salgado | [25 empty] | 100% | Teamwork and intercommunocation. | 2 | 100% | 2
2 | Identification of opportunities to obtain resources for Centers' equipement (Mexicali, Tijuana) | 5,12 | Dra. Cantellano, MBA Paulina Vargas, MFC Lisette Salgado | [25 empty] | 100% | Resources were obtained for ENDEAVOR and Asian Forum. | 2 | 100% | 2
3 | To follow Up study IMPULSA Alumni (Mexicali, Tijuana) | 9 | Dr. Cantellano, Lic. Ernesto Romero, Lic. Erick Macip | [25 empty] | Aplplication of 100 surveys | Not done | 1 |  | 0
4 | To foster participation of students, instructors and entrepreneurs in networks as well as in the relationship with entrepreneurial organisms and educational institutions. | 9 | Dr. Cantellano | [25 empty] | 100% of instructors and students involved in entrepreneurial programs | We continue being part of the Networks: espacio vanguardia and AMCDPE | 2 | 100% | 2
5 | Participation in the media to inform the community about the CENTER activities (Mexicali, Tijuana) | 11 | Dr. Cantellano, Lic. Adrriana Eguía, MFC Lisette Salgado, MBA Paulina Vargas | [25 empty] | 20 presentations in the media | Diffusion of all programs events. | 2 | 100% | 2
6 | To foster the meeting of local businessmen with our entrepreneurs to establish entrepreneurial bonds and tutoring. (Mexicali Tijuana) | 11 | Dr. Cantellano , Lic. Adriana Eguía, MFC Lisette Salgado | [25 empty] | 5 visits per campus | Counseling by tutors and instructors of the financial area | 2 | 100% | 2
7 | Publishing of the monthly article of COMCE | 11 | Dr. Cantellano, Lic. Ernesto Romero | [25 empty] | 16 articles published | Continuing | 1 | 100% | 1
8 | To establish a formal bond with the State Government for the entrepreneurs benefit (Mexcali, Tijuana) | 9, 11, 12 | Dr. Cantellano, Lic. Adriana Eguia, MFC Lisette Salgado | [25 empty] | 100% | Close relationship with SEDECO, FIDEM and CEDEM | 2 | 100% | 2
Tactic Level
| Activities | Impact on objetive | Responsible | Resources | Jul. 1: Jul.; Aug. 1: Aug.; Sep. 1: Sep.; Oct. 1: Oct.; Nov. 1: Nov.; Dec. 1: Dec. | Expected Outcome (Goal) | Comments | Importance | Achieved Outcome (from goal) | Assessment
| (actions, projects) |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
9 | Organization and follow up of monthly reunions of the entrepreneurial board as counselors of CDE (Mexicali, Tijuana) | 11 | Dr. Cantellano, MBA Paulina Vargas, MFC Lisette Salgado | [25 empty] | 15 counselors, with 4 reunions | They were carried out together with the Asian Forum and ENDEAVOR panel | 2 | 100% | 2 | bar: Aug. 1 to Dec. 4
10 | Creation of the Coast Zone of the Center | 9, 11 | Dr. Cantellano, MFC Lisette Salgado | [25 empty] | 100% | It was integrated and with espaces in the equipping process | 2 | 100% | 2 | bar: Aug. 1 to Dec. 4
11 | To integrate an academic group of research at system level focused on companies (participation of the study of cultural diversity in companies on the Mexican Northern Border and its impact in competitiveness and quality of labor life) | 9,11,12 | Dr. Cantellano, MBA. Cinthia Carrasco | [25 empty] | 100% | Integrated with the Academy of the School of A and N and network with other universities | 2 | 100% | 2 | bar: Aug. 1 to Dec. 4
20
Operative level
| Activities | Impact on objective | Responsible | DATE | Jul. 1: Jul.; Aug. 1: Aug.; Sep. 1: Sept.; Oct. 1: Oct.; Nov. 1: Nov.; Dec. 1: Dec. | Expected Outcome (Goal) | Comments | Importance | Achieved Outcome (from goal) | Assessment
| (actions, projects) |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | To organize guided tours in Spanish and English to local companies with University students | 8 | Lic. Teresa Escárcega | [25 empty] | 12 Visits | 13 visits organized in Mexicali and Tijuana | 1 | 100% | 1
2 | To organize conferences in Spanish and English for University students with local businessmen | 8 | Lic. Teresa Escárcega | [25 empty] | 15 Conferences | 16 Conferences in Tijuana, Ensenada and Mexicali, including Coorporate Government and Empreser | 3 | 100% | 3
3 | Application of the program Young Entrepreneurs in all highschool 5th semester students of Mexicali campus workshop in the subject Administration I | 8 | Lic. Ernesto Romero,M.A. Gina Villalba | [25 empty] | 150 High school students | 241 from high school in Mexicali and Tijuana with 32 teams. | 3 | 100% | 3
4 | Application of the MESE program to all the university 1st semester students in the subject of Globalization and Economic Development | 8 | Lic. Ernesto A. Romero, Lic. Erck Macip, Lic. Caridad Medina | [25 empty] | 419 University students | 425 students in the three campuses with137 teams. | 3 | 100% | 3
5 | Application of Young Entrepreneurs programs to all the 7th semester university students of LAM, LNI, LAE and CP of Mexicali, Tijuana and Ensenada campus in the subject of Entrepreneur Development | 8 | Lic. Ernesto A. Romero, Lic. Erck Macip, Lic. Caridad Medina | [25 empty] | 127 students | 151 students which were the total amount of registered students in the three campus | 1 | 100% | 1
Operative level
| Activities | Impacto al objetivo | Responsable | FECHA | Jul. 1: Jul.; Aug. 1: Aug.; Sept. 1: Sept.; Oct. 1: Oct.; Nov. 1: Nov.; Dec. 1: Dec. | Expected Outcome (Goal) | Comments | Importance | Achieved Outcome (from goal) | Assessment
| (actions, projects) |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
6 | Pilot of the Young Entrepreneurs program for first stage engineering students of Ensenada campus | 8 | Lic. Caridad Medina | [25 empty] | 25 Students | The pilot program was carried out with 26 students | 3 | 100% | 3
7 | Organization for company's visit at a state level with each campus students in inter Cetys groups. | 8 | Lic. Ernesto A. Romero | [25 empty] | 1 Visit | Wasn't carried out because of budget problems | 1 | 0% | 0
8 | Organization and presentation of Entrepreneurial Development Center of Cetys University System to all new students in University, Mexicali campus | 8 | Lic. Ernesto A. Romero | [25 empty] | 1 Presentation | 2 presentations Mexicali and Tijuana | 3 | 100% | 3
9 | To participate in national and international contests that function as entrepreneurial encouragement for Cetys students such as Banks in Action | 7,8 | Lic. Ernesto A. Romero, M.A. Gina Villalba | [25 empty] | 20 participating students | 42 students with Banks in Action and 43 with Latin Entrepreneur | 2 | 100% | 2
10 | To participate in the Entrepreneurial International Forum, Guatemala Edition | 7,8 | Lic. Ernesto A. Romero, Lic. Erck Macip, Lic. Caridad Medina | [25 empty] | 20 participating students | Wasn't carried out because of budget problems | 1 | 0% | 0
11 | Presentation of Semester Work plans to Members of the Entrepreneurial Academic Board | 9 | Lic. Ulysses Moreno | [25 empty] | 1 Presentation | Was carried out at the beginning of the semester | 2 | 100% | 2
Operative level
| Activities | Impact on objective | Responsible | DATE | Jul. 1: Jul.; Aug. 1: Aug.; Sept. 1: Sept.; Oct. 1: Oct.; Nov. 1: Nov.; Dec. 1: Dec. | Expected Outcome (Goal) | Comments | Importance | Achieved Outcome (from goal) | Evaluación
| (actions, projects) |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
12 | Organization of visits to classrooms in high school, university, department of graduate students, linkage department and language center and internal and external diffusion of Cetys EmpreSer Module | 8 | Lic. Ulysses Moreno | [25 empty] | • 8 visits to university. • 10 visits to graduate students department. • 3 visits to technical courses, diploma courses and seminars. • 13 special events. | 8 visits to university, 13 to master, 1 to managerial majors, 3 to technical and 14 special events | 1 | 100% | 1
13 | Participation in the media to report advances of Cetys EmpreSer Module | 11 | Lic. Ulysses Moreno | [25 empty] | 7 spaces in the Media | Frequent presentations in the media, press, radio and TV | 1 | 100% | 1
14 | Trimester follow up to successful Cetys EmpreSer cases and report of required counceling | 11 | Lic. Ulysses Moreno | [25 empty] | 6 Trimester Follow ups | Goal Accomplished | 1 | 100% | 1
15 | To organize the Semester Press Conference to present new entrepreneurs | 11 | Lic. Ulysses Moreno | [25 empty] | 1 Press conference | Carried out on November 27, 2008 | 1 | 100% | 1
16 | Company opening | 9,11 | Lic. Ulysses Moreno | [25 empty] | 10 new companies | 9 opened up to November | 2 | 90% | 1.8
17 | Promotion of Endeavor Center services at a state level | 9,11 | Lic. Adriana Eguía | [25 empty] | 4 Promotions | 48 promotions | 1 | 100% | 1
18 | Obtention and selection of new tutors | 9,11 | Lic. Adriana Eguía | [25 empty] | 10 New Tutors | 18 new mentors | 1 | 100% | 1
19 | Obtention and selection of consultants for Endeavor services | 9,11 | Lic. Adriana Eguía | [25 empty] | 5 Consultants | 4 consultants | 2 | 90% | 1.8
20 | Promotion in the media of the selected Endeavor projects | 11 | Lic. Adriana Eguía | [25 empty] | 5 Spaces in the Media | 8 in Mexicali, 4 in Tijuana and 2 in Ensenada | 1 | 100% | 1
Operative level
| Activities | Impact on objective | Responsible | DATE | Jul. 1: Jul.; Aug. 1: Aug.; Sept. 1: Sept.; Oct. 1: Oct.; Nov. 1: Nov.; Dec. 1: Dec. | Expected Outcome (Goal) | Comments | Importance | Achieved Outcome (from goal) | Assessment
| (actions, projects) |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
21 | To establish standards of Endeavor candidate companies | 10 | Lic. Adriana Eguía | [25 empty] | 5 files | The standards of 8 files were established | 1 | 100% | 1
22 | Organization and presentation of Entrepreneurs Panel. | 9,11 | Lic. Adriana Eguía | [25 empty] | 1 Entrepreneurs Panel | November 29 ENDEAVOR panel in Tijuana | 1 | 100% | 1
| Invitation to instructors and students to be spectators in the company presentation and in the Endeavor company selection | 8,9,11 | Lic. Adriana Eguía | [25 empty] | 20 participating students | Attendance achieved | 1 | 100% | 1
23 | Corporate Government Conferences | 9,11 | MFC Lisette Salgado Patiño | [25 empty] | 2 conferences | 1 carried out | 2 | 50% | 1
24 | Presentation of CDE proposed structure | 9,11 | Dra. Delia Cantellano | [25 empty] | 1 presentation | In process in Tijuana | 1 | 100% | 1
[31 empty] | 100 |  | 94
Filled out at the end of the semester

## Sheet1
Lista de Verificación para certificación
Requisito | Esta Documentado | Se tiene difundido | Esta autorizado | Se mide el proceso | Existen Indicadores | Registro | Formatos | Se tiene | "Amigable para el Cliente"
1. Evidencia de Documentación:
Cédula de registro como miembro activo de la AMCDPE
Manual de organización
Plan estratégico o Plan Operativo Anual
Identificar y segmentar a los clientes, mercados y asociados
importantes
Programa de capacitación interna
Mision
Visión
Valores de la organización
Sistema de comunicación interna
Expedientes del personal operativo
Expedientes del personal administrativo
Plantilla de consultores
Casos de éxito
Sistema de quejas y sugerencias
Encuesta de evaluación de los servicios
Procedimientos:
1. Asistencia a negocios (desde que se tiene el primer contacto con el cliente hasta que se proporciona un servicio)
2. Asesoría
3. Capacitación personal interno
4. Capacitación a clientes
5. Planeación estratégica
6. Seguimiento y evaluación de los servicios
7. Identificación de las necesidades de los clientes
8. Medición del desempeño
9. Medición del impacto económico
10. Acciones correctivas y preventivas
11. Selección y recopilación de datos
12. Gestión de recursos (Financiamiento)
13. Clima laboral
14. Selección y contratación de personal
15. Asignación y supervisión del trabajo
16. Comunicación
17. Innovación organizacional
18. Revisión de la Dirección
2. Imagen e Infraestructura:
Imagen corporativa
Área de Recepción
Sala de espera ( asientos para el cliente)
Área de Atención al Cliente
Sala de Juntas (capacidad mínima para 15 personas)
3. Tecnología:
Contar con sistemas que aseguren un ejercicio fiscal y
contractual sano de sus programas.
Red de internet
Base de datos de clientes
Sistema de comunicación con el cliente
4. Recursos Administrativos:
Identidad propia y presupuesto por separado (en el caso depertenecer a una institución)
Estar vinculados a una Institución de Educación
Estrategia de búsqueda de financiamiento
5. Recurso Humano:
Director
Consultores certificados en uno o más modelos (CONOCER,
CONACYT, NOM, SBDC, etc.)
Recepcionista
Asistente administrativo
Becario
6. Ofrecer servicios a los clientes:
Mercadotecnia
Estudios de factibilidad
Comercio internacional
Habilidades gerenciales
Financiamiento
Tecnología
Licitaciones para ventas a gobierno
Formación de capital de riesgo
Desarrollo rural
Proyecto de inversión
Capacitación específica
|  | Elaboró |  |  | Autorizó
|  | Coordinación de Calidad |  |  | Dirección General