## FLUJO EFVO COMPARATIVO NOV.2010
| CETYS UNIVERSIDAD CAMPUS TIJUANA | [17 empty] | CETYS UNIVERSIDAD CAMPUS TIJUANA | [17 empty] | CETYS UNIVERSIDAD CAMPUS TIJUANA
| BIBLIOTECA Y CENTRO DE INFORMACION LUIS FIMBRES MORENO | [14 empty] | BIBLIOTECA Y CENTRO DE INFORMACION LUIS FIMBRES MORENO | [17 empty] | BIBLIOTECA Y CENTRO DE INFORMACION LUIS FIMBRES MORENO
| PROYECTO DE ACTUALIZACION Y AMPLIACION | [16 empty] | PROYECTO DE ACTUALIZACION Y AMPLIACION | [17 empty] | PROYECTO DE ACTUALIZACION Y AMPLIACION
| Al 31 DE OCTUBRE DE 2010 | [16 empty] | Al 22 DE OCTUBRE DE 2010 | [17 empty] | Al 22 DE OCTUBRE DE 2010
| (cantidades en pesos) | [14 empty] | (cantidades en pesos) | [17 empty] | (cantidades en pesos)
DATOS REALES al 31.Oct.10
t.c.
| CONCEPTOS | EJERCIDO 2009 | REAL al 31.Oct.10 | PRESUPUESTO TOTAL PROYECTO | 1 | PROYECTADO NOVIEMBRE 2010 | PROYECTADO DICIEMBRE 2010 | PROYECTADO ENERO 2011 | PROYECTADO FEBRERO 2011 | SEGUNDO SEMESTRE 2010 |  | TOTAL ACUMULADO | CONCEPTOS | SEPTIEMBRE 2010 | Sem. 3 Octubre | Sem. 4 Octubre | OCTUBRE 2010 | Sem. 1 Noviembre | Sem. 2 Noviembre | Sem. 3 Noviembre | Sem. 4 Noviembre | NOVIEMBRE 2010 | Sem. 1 Diciembre | Sem. 2 Diciembre | Sem. 3 Diciembre | Sem. 4 Diciembre | DICIEMBRE 2010 | ACUMULADO 2010 | CONCEPTOS | Sem. 1 Enero 2011 | Sem. 2 Enero 2011 | Sem. 3 Enero 2011 | Sem. 4 Enero 2011 | ENERO 2011 | Sem. 1 Febrero 2011 | Sem. 2 Febrero 2011 | Sem. 3 Febrero 2011 | Sem. 4 Febrero 2011 | FEBRERO 2011 | SEGUNDO SEM 2011 | ACUMULADO 2011 | ACUMULADO TOTAL 2010-2011
12.2
| INGRESOS |  |  |  | 12.5 | [7 empty] | INGRESOS | [15 empty] | INGRESOS
1 | DONATIVO FAM. FIMBRES |  | 492000 | 3660000 |  | 732000 | 610000 | 915000 | 911000 |  |  | 3660000 | DONATIVO FAM. FIMBRES |  | 492000 |  | 492000 |  |  | 732000 |  | 732000 |  |  |  | 610000 | 610000 | 1834000 | DONATIVO FAM. FIMBRES |  |  | 915000 |  | 915000 |  |  | 911000 |  | 911000 |  | 1826000 | 3660000
2 | DONATIVO G. ASTIAZARAN |  | 60000 | 122000 |  | 0 | 0 | 62000 | 0 |  |  | 122000 | DONATIVO G. ASTIAZARAN |  | 60000 | 0 | 60000 | 0 |  |  |  | 0 |  |  |  |  | 0 | 60000 | DONATIVO G. ASTIAZARAN |  | 62000 |  |  | 62000 |  |  |  |  | 0 |  | 62000 | 122000
3 | CENA DE GALA |  | 107304.99 | 1220000 |  | 400000 | 380000 | 332695 | 0 |  |  | 1219999.99 | CENA DE GALA | 68820 | 38484.99 |  | 38484.99 |  |  |  | 400000 | 400000 | 100000 | 150000 | 100000 | 30000 | 380000 | 887304.99 | CENA DE GALA |  | 220000 |  | 112695 | 332695 |  |  |  |  | 0 |  | 332695 | 1219999.99
3 | REMANENTES CETYS 2010-I |  | 275000 | 275000 |  |  | 0 |  |  |  |  | 275000 | REMANENTES CETYS 2010-I | 275000 | [13 empty] | 275000 | REMANENTES CETYS 2010-I | [11 empty] | 0 | 275000
4 | OTROS DONATIVOS |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | REMANENTES CETYS 2010-II | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | REMANENTES CETYS 2010-II |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
| SUB-TOTALES DE INGRESOS |  | 934304.99 | 5277000 |  | 1132000 | 990000 | 1309695 | 911000 |  |  | 5276999.99 | SUB-TOTALES DE INGRESOS | 343820 | 590484.99 | 0 | 590484.99 | 0 | 0 | 732000 | 400000 | 1132000 | 100000 | 150000 | 100000 | 640000 | 990000 | 3056304.99 | SUB-TOTALES DE INGRESOS | 0 | 282000 | 915000 | 112695 | 1309695 | 0 | 0 | 911000 | 0 | 911000 |  | 2220695 | 5276999.99
| TOTAL INGRESOS |  | 934304.99 | 5277000 |  | 2066304.99 | 3056304.99 | 4365999.99 | 5276999.99 | 5276999.99 |  | 5276999.99 | TOTAL INGRESOS | 343820 | 934304.99 | 934304.99 | 934304.99 | 934304.99 | 934304.99 | 1666304.99 | 2066304.99 | 2066304.99 | 2166304.99 | 2316304.99 | 2416304.99 | 3056304.99 | 3056304.99 | 3056304.99 | TOTAL INGRESOS | 3056304.99 | 3338304.99 | 4253304.99 | 4365999.99 | 4365999.99 | 4365999.99 | 4365999.99 | 5276999.99 | 5276999.99 | 5276999.99 | 5276999.99 |  | 5276999.99
| CONCEPTOS | EJERCIDO 2009 | REAL al 31.Oct.10 | PRESUPUESTO TOTAL PROYECTO | [8 empty] | CONCEPTOS | SEPTIEMBRE 2010 | Sem. 3 Octubre | Sem. 4 Octubre | OCTUBRE 2010 | Sem. 1 Noviembre | Sem. 2 Noviembre | Sem. 3 Noviembre | Sem. 4 Noviembre | NOVIEMBRE 2010 | Sem. 1 Diciembre | Sem. 2 Diciembre | Sem. 3 Diciembre | Sem. 4 Diciembre | DICIEMBRE 2010 | ACUMULADO 2010 | CONCEPTOS | Sem. 1 Enero 2011 | Sem. 2 Enero 2011 | Sem. 3 Enero 2011 | Sem. 4 Enero 2011 | ENERO 2011 | Sem. 1 Febrero 2011 | Sem. 2 Febrero 2011 | Sem. 3 Febrero 2011 | Sem. 4 Febrero 2011 | FEBRERO 2011 | SEGUNDO SEM 2011 | ACUMULADO 2011 | ACUMULADO TOTAL 2010-2011
| EGRESOS |  |  |  | 12.5 | [7 empty] | EGRESOS | [15 empty] | EGRESOS
5 | OBRA CIVIL (Remodelación) |  |  | 1561875 |  | 624750 | 624750 | 156187.5 | 156187.5 |  |  | 1561875 | OBRA CIVIL (Remodelación) |  |  |  | 0 |  | 624750 |  |  | 624750 |  | 312375 |  | 312375 | 624750 | 1249500 | OBRA CIVIL (Remodelación) |  | 156187.5 |  |  | 156187.5 | 156187.5 |  |  |  | 156187.5 |  | 312375 | 1561875
6 | MOBILIARIO |  |  | 831922.875 |  | 499153.725 | 166384.575 | 83192.2875 | 83192.2875 |  |  | 831922.875 | MOBILIARIO |  |  |  | 0 |  |  | 499153.725 |  | 499153.725 |  |  | 166384.575 |  | 166384.575 | 665538.3 | MOBILIARIO |  |  | 83192.2875 |  | 83192.2875 |  | 83192.2875 |  |  | 83192.2875 |  | 166384.575 | 831922.875
7 | INFRAESTRUCTURA DE TECNOLOGIAS Y EQPO COMPUTO |  | 162432 | 987242.25 |  | 0 | 30427.0425 | 0 | 794382.53 |  |  | 987241.5725 | INFRAESTRUCTURA DE TECNOLOGIAS Y EQPO COMPUTO | 162432 |  |  | 0 |  |  |  |  | 0 | 30427.0425 |  |  |  | 30427.0425 | 192859.0425 | INFRAESTRUCTURA DE TECNOLOGIAS Y EQPO COMPUTO |  |  |  |  | 0 | 505380.78 |  | 289001.75 |  | 794382.53 |  | 794382.53 | 987241.5725
8 | FACHADA DE BIBLIOTECA Y MURAL |  | 122515 | 312500 |  | 0 | 189985 | 0 | 0 |  |  | 312500 | FACHADA DE BIBLIOTECA Y MURAL | 0 | 122515 |  | 122515 | 0 |  |  |  | 0 |  | 189985 |  |  | 189985 | 312500 | FACHADA DE BIBLIOTECA Y MURAL |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 312500
9 | ACERVO |  | 106509.22 | 1250000 |  | 100000 | 312500 | 250000 | 162500 | 318491 |  | 1250000.22 | ACERVO | 4453.71 | 76066.39 | 25989.12 | 102055.51 |  |  |  | 100000 | 100000 |  | 312500 |  |  | 312500 | 519009.22 | ACERVO |  |  |  | 250000 | 250000 |  |  |  | 162500 | 162500 | 318491 | 730991 | 1250000.22
;l | SUB-TOTALES DE EGRESOS | 0 | 391456.22 | 4943540.125 |  | 1223903.725 | 1324046.6175 | 489379.7875 | 1196262.3175 | 318491 |  | 4943539.6675 | SUB-TOTALES DE EGRESOS | 166885.71 | 198581.39 | 25989.12 | 224570.51 | 0 | 624750 | 499153.725 | 100000 | 1223903.725 | 30427.0425 | 814860 | 166384.575 | 312375 | 1324046.6175 | 2939406.5625 | SUB-TOTALES DE EGRESOS | 0 | 156187.5 | 83192.2875 | 250000 | 489379.7875 | 661568.28 | 83192.2875 | 289001.75 | 162500 | 1196262.3175 | 318491 | 2004133.105 | 4943539.6675
| TOTAL EGRESOS |  | 391456.22 | 4943540.125 |  | 1615359.945 | 2939406.5625 | 3428786.35 | 4625048.6675 | 4943539.6675 |  | 4943539.6675 | TOTAL EGRESOS | 166885.71 | 365467.1 | 391456.22 | 391456.22 | 391456.22 | 1016206.22 | 1515359.945 | 1615359.945 | 1615359.945 | 1645786.9875 | 2460646.9875 | 2627031.5625 | 2939406.5625 | 2939406.5625 | 2939406.5625 | TOTAL EGRESOS | 2939406.5625 | 3095594.0625 | 3178786.35 | 3428786.35 | 3428786.35 | 4090354.63 | 4173546.9175 | 4462548.6675 | 4625048.6675 | 4625048.6675 | 4943539.6675 |  | 4943539.6675
| REMANENTE |  | 542848.77 | 333459.875 |  | 450945.045 | 116898.4275 | 937213.64 | 651951.3225 | 333460.3225 | 0 | 333460.3225 | REMANENTE | 176934.29 | 401952.18 | 542848.77 | 542848.77 | 542848.77 | -81901.23 | 150945.045 | 450945.045 | 450945.045 | 520518.0025 | -144341.9975 | -210726.5725 | 116898.4275 | 116898.4275 | 116898.4275 | REMANENTE | 116898.4275 | 242710.9275 | 1074518.64 | 937213.64 | 937213.64 | 275645.36 | 192453.0725 | 814451.3225 | 651951.3225 | 651951.3225 | 333460.3225 | 0 | 333460.3225
Nota 1. Este presupuesto incluye IVA 11%
| Nota 2. Este presupuesto se presente en pesos. |  |  |  |  | PENDIENTE LIBERAR O NO LOS $ 525 MIL PESOS DE REMANENTES 2010-II
Con t.c. de ingresos promedio de 12.20 y de egresos de 12.50
| Nota 3. Falta definir la inversion de $ 245 mil pesos de proyecto WASC de Remanentes 2010-II ($ 735 mil pesos) |  |  |  |  | $ 280 MIL CONSTRUCCION OBRA CIVIL (2010-II).
| Nota 4. Cena de Gala 2010 se estima la cobranza del evento 2010 y 2011. |  |  |  |  | $ 245 MIL LIC ACERVO BIBLIOGRAF (2010-II).
Note on E14: alejandra.guerrero: T.C. $ 12.20 X 1 $ 300,000.00 DLLS
Note on E15: alejandra.guerrero: T.C. $ 12.20 X 1 $ 10,000.00 DLLS
Note on E16: alejandra.guerrero: T.C. $ 12.20 X 1 $ 100,000.00 DLLS
Note on E17: *PRESUPUESTO REMANENTE 2010-I: $ 735,000.00 210,000.00 Proy Institucionales Mxl-Tij 275,000.00 Lic Acervo Electronc 280,000.00 Construccion Proyecto Biblioteca. En 2010-I Se ejercieron $ 250,000.00 pesos para Acervo (lo presupuestado) más otros $ 250,000.00 pesos de los $ 735 mil presupuestados y no ejercidos. $ 275,000.00 corresponden a Proyecto WASC Biblioteca sin ejercer en el 2010-I. Correspoonde a Construcción. $ 280 mil pesos (Con dif de $ 5 mil pesos).
Note on E18: *PRESUPUESTO REMANENTE 2010-II: $ 735,000.00 210,000.00 Proy Institucionales Mxl-Tij 275,000.00 Lic Acervo Electronc. Pend definir si se ejerc. 280,000.00 Construccion Proyecto Biblioteca.
Note on U26: alejandra.guerrero: 40% $ 1'658 MIL
Note on V26: alejandra.guerrero: 40% $ 1'658 MIL
Note on X26: alejandra.guerrero: 20% $ 1'658 MIL
Note on Z26: alejandra.guerrero: 20% $ 1'658 MIL
Note on AA26: alejandra.guerrero: 20% $ 1'658 MIL
Note on AC26: alejandra.guerrero: 20% $ 1'658 MIL
Note on AH26: alejandra.guerrero: 10% $ 1'658 MIL
Note on AL26: alejandra.guerrero: 10% $ 1'658 MIL
Note on V27: alejandra.guerrero: 60% $ 827,000.00 M.N.
Note on W27: alejandra.guerrero: 60% $ 827,000.00 M.N.
Note on AB27: alejandra.guerrero: 20% $ 827,000.00 M.N.
Note on AI27: alejandra.guerrero: 10% $ 827,000.00 M.N.
Note on AM27: alejandra.guerrero: 10% $ 827,000.00 M.N.
Note on Q28: alejandra.guerrero: ANTENAS DE SEGURIDAD
Note on R29: alejandra.guerrero: fachada de biblioteca $ 10 mil dlls

## 1ERA FASE PROY BIB 31.OCT.09
CETYS UNIVERSIDAD CAMPUS TIJUANA
FLUJO DE EFECTIVO DE CAMPAÑAS DE CAPITAL
DEL 1 DE ENERO AL 31 DE DICIEMBRE DE 2008
(DOLARES)
T.C.
| CAMPAÑAS DE CAPITAL |  |  |  | REAL ACUML ENE-JULIO 2008 | PPTO 2008 ENE-DIC
| SALDO INICIAL EFECTIVO 2008 |  |  |  | #REF!
| DONATIVOS (Eventos Productivos 2008) |  |  |  | #REF! | 40000
| DONATIVOS CAMPAÑA 2008 |  |  |  | #REF! | 365000
0
| TOTAL DE INGRESOS CAMPANA 2008 |  |  |  | #REF! | 405000
EGRESOS CAMPANA 2008
| ACERVO BIBLIOGRAFICO (Base de datos, revistas) |  |  |  | 0 | 50000
| AREAS VERDES LANSCAPING |  |  |  | 0 | 30000
| BECAS TALENTO |  |  |  | #REF! | 80000
| EQUIPO AUDIOVISUAL |  |  |  | 0 | 45000
| EQUIPAMIENTO DEPORTIVO, UNIFORMES |  |  |  | 0 | 35000
| EQUIPO COMPUTO AREA ACADEMICA |  |  |  | 0 | 50000
| MOBILIARIO SALONES |  |  |  | 0 | 70000
| SISTEMA DE SEGURIDAD BIBLIOTECA |  |  |  |  | 25000
| COSTO DE LA COMPAÑA |  |  |  | #REF! | 20000
| SUB-TOTAL DE EGRESOS CAMPANA 2008 |  |  |  | #REF! | 405000
EGRESOS CAMPANA 2007
0
0
| REMODELACION SALONES (Contacto en aulas) |  |  |  | #REF!
ACERVO BIBLIOGRAFICO
| BECAS TALENTO |  |  |  | #REF!
| PLAZA CIVICA |  |  |  | #REF!
| SUB-TOTAL DE EGRESOS CAMPANA 2007 |  |  |  | #REF! | 0
| TOTAL EFECTIVO NETO CAMPANA AL 30 DE JUNIO 08 |  |  |  | #REF! | 0
CETYS UNIVERSITY CAMPUS TIJUANA
LIBRARY AND INFORMATION CENTER LUIS FIMBRES MORENO
UPDATE AND EXTENSION PROJECT
TO OCTOBER 31 2009
(amounts in US Dollars)
| CONCEPTS | REAL INVESTMENT PHASE 1 TO OCT 31 2009 | BUDGET PHASE 1 | VARIATIONS | BUDGET PHASE 2 | BUDGET PHASE 3 | TOTAL BUDGET PROJECT
0
INCOME
1 | [6 empty] | 0
2 | SURPLUS 2009-I | 40001 | 40000.6154 | -0.38462
3 | SURPLUS 2009-II | 40000 | 39999.6154 | -0.38462
8 | SUB-TOTAL INCOME | 80001 | 80001.2308 | -0.23077 | 0 | 0 | 0
9 | TOTAL INCOME ACCRUED | 80001 | 80001.2308 | -0.23077 |  | 0 | 0
EXPENDITURE
| CIVIL WORK (Remodeling) | 35491.1808 | 43597.22 | 8106.0392 | 45350.45 | 27390.45 | 116338.12 | 105761.9273
| FURNITURE | 29782.1538 | 23147.22 | -6634.9338 | 73041.72 | 8483.78 | 104672.72 | 95157.0182
| INFRASTRUCTURE TECHNOLOGY & COMPUTER EQUIPMENT | 7819.43 | 8144.477 | 325.047 | 25354.736 | 32978 | 66477.213 | 60433.83
| CAMPAIGN COST | 0 | 0 | 0 | 0 | 7000 | 7000 | 6363.6364
0
| SUB-TOTAL EXPENDITURE | 73092.7646 | 74888.917 | 1796.1524 | 143746.906 | 75852.23 | 294488.053 | 267716.4118
| TOTAL EXPENDITURE ACCRUED | 73092.7646 | 74888.917 |  | 143746.906 | 219599.136 | 294488.053 | 294488.053
23 | SURPLUS ACCRUED IN CASH | 6908.2354 | 5112.3138
294487.75
| Note 1. This budget includes VAT 10% | [6 empty] | -0.303
Note 2. This budget is in US Dollars
Note 3. In August one part of the first phase of the project, started, Civil Work and
part of infrastructure technology. With surplus funding Campus Tijuana.
EXPENDITURE
| Balance without accounting to Oct. 31, 2009 & Nov.05, 2009 | 681490.68
| Records in November 2009 (outstanding) Computing | 53822.6
| Records in November 2009 (outstanding) A/C | 8908.9
| Records in November 2009 (outstanding) Shelves | 109230
| Records in November 2009 (outstanding) Furniture 50% | 111032.35
964484.53
INCOME
| Surplus | 1050000
| VARIATION | 85515.47
| CASH BALANCE ON PROYECT CI AND B | 89807.06
Note on H31: aguerrero: EL COSTO DE LA CAMPAÑA ES ESTIMADO XQ POR PARTE DE AVANCE NO RECIBIMOS PROPUESTA. MZO.28,2008

## OBRA CIVIL
CIVIL WORK
QUOTATIONS
ITEMS |  |  |  | TOTAL ARQ. CARLOS | TOTAL ARQ. ELIO | Metric |  | total remodelación 2010 | diferencias VS nuevo presupuesto |  |  | GENSA (A/C) | RAIN (A/C)
2 | EXTERNAL WORKS |  |  | 30813.66 | 38692.5 | 33548.165 |  | 19832.5 | 18860 |  | MAS DEMOLICIONES Y ACARREOS
5 | METALS |  |  | 0 | 37600 | 35536.3 | PENDINETE POR COTIZAR | 0 | 37600 |  | ESTRUCTURA PARA PODER DEMOLER
6 | WALLS AND CEILINGS |  |  | 238330.421 | 265079.997 | 237850.581 |  | 120008.637 | 145071.36 |  | MAYOR METROS DE PLAFON Y MURO
7 | DOORS AND WINDOWS |  |  | 164458.5 | 95008 | 126052.38 |  | 48721.0568 | 46286.9432 |  | UNA PUERTA DE CRISTAL TEMPLADO 69 K
8 | FINISH |  |  | 449437.426 | 429278.0818 | 437064.353 |  | 192970.7954 | 236307.2863 |  | LOSETA EN AREA DE ENTRADA, AULA MAGNA Y CICULACION
10 | TOILETS AND LAVATORIES |  |  | 70193.99 | 97731.5846 | 73498.63 | NO INCLUYE EXCAVACIONES NI RELLENO | 97334.3036 | 397.281 |  | SE CAMBIO AL SANITARIO DE FLUXOMETRO
11 | AIR CONDITIONING |  |  | 0 |  | 212125.45 | PENDINETE POR COTIZAR | 131121.892 | -131121.892 |  | REORGANIZACION DE DUCTERIA POR NUEVAS AREAS | 209225 | 249425
12 | HYDRAULIC SYSTEM |  |  | 92672.358 | 44238.2 | 57199.234 |  | 48914.249 | -4676.049
14 | ELECTRICAL INSTALLATION |  |  | 195046.73 | 129549.74 | 113192.47 |  | 126996.639 | 2553.101 |  | REUBICACION DE UN TABLERO ELECTRICO
|  |  | TOTAL BUDGET | 1240953.085 | 1137178.1034 | 1326067.563 | 0 | 785900.0728 | 351278.0306 | 0 | 0 | 209225 | 249425
|  |  | VAT | 136504.8393 | 125089.5914 | 145867.4319 | 0 | 86449.008 | 38640.5834 | 0 | 0 | 23014.75 | 27436.75
|  | TOTAL CONSTRUCTION IN PESOS |  | 1377457.9243 | 1262267.6948 | 1471934.9949 | 0 | 872349.0808 | 389918.614 | 0 | 0 | 232239.75 | 276861.75
|  | TOTAL CONSTRUCTION IN Dlls |  | 110196.6339 | 100981.4156 | 117754.7996 | 0 | 69787.9265 | 31193.4891 | 0 | 0 | 18579.18 | 22148.94
| TOTAL DE PARTIDAS QUE AMBOS COTIZARON |  |  | 1240953.085 | 1099578.1034 | 1078405.813 | #REF!
|  |  | TO CONTRACT |  | 119560.5956 | DLLS
CONCLUSIONES: AMBAS COTIZACIONES CUENTAN CON PRECIOS DE MERCADO, LA DIFERENCIA A FAVOR DE EL PRESUPUESTO DEL ARQ. CARLOS PEÑA ESTRIBA EN LOS COSTOS PENDIENTES DE ESTRUCTURA METALICA, EXCAVACIONES Y RELLENO EN TUBERIAS DE DRENAJE Y SISTEMA DE A/C, SI SUMAMOS UNICAMENTE LAS PARTIDAS QUE LOS DOS PROVEEDORES TIENE COTIZADAS EXISTE UNA DIFERENCIA ENTRE AMBOS DE $983.46 PESOS

## MOBILIARIO
FURNITURE FOR LIBRARY REMODELING | [8 empty] | PROVIDER
Budget for October Octubre 2010 | [8 empty] | OficeMart |  | JFA | GENSA | Gusmar | COMANDER | J FLORES
Furniture | Description | Quantity | Dimensions | Proveedor | Model | Foto | Proveedor | Costo | Total | Total | Total | Total
Training Room
Table for students | Education Workstations | 12 | 60"x24"x 29.5" |  | ED2460 HON |  | OficeMart | 2835.55 |  |  | 33144
Individual table for student | Individual table for students | 6 | 36"x24"x29.5" |  | ED2436G HON |  | OficeMart | 2677.69 |  |  | 14892
Table accessories | Pipelines | 1 | - |  | VARIOS |  | OficeMart | 14208.4 |  |  | 18889
Contacts | Workshop table | 6 | - |  | ULSG3 |  | OficeMart | 4383.49
Chairs | Stackable chairs | 30 | - |  | STC 3050 |  | OficeMart | 659.61 | 19788.3
High chair with wheels without armrests | Chair for Teacher | 1 | - |  | B1690 |  | OficeMart | 898.07 | 898.07
Workstation for teacher |  | 1 | 48"x24"x40" |  | EDC41J | Foto Muebles\Estación maestros.JPG | Ofice Mart | 1114.35 | 1114.35 |  | 13929.375
Table accessories | [6 empty] | Ofice Mart | 18054.8
Workstation for teacher |  | 1 | 48"x24"40" |  | - |  | GAYLOR | 13929.375 |  |  |  | 8907.75
Blackboard | Porcelain white board | 1 | 2.40 x 1.20 mts |  | - |  | Gusmar | 2615 |  |  |  |  | 2615
[8 empty] | TOTAL | 21800.72 |  | 80854.375 | 8907.75 | 2615
Electronic Room
Table for students | Workstation for Students | 10 | 66"x24"x 29.5" |  | 66582 HON |  | OficeMart | 4645.19 |  |  | 46900
Keyboard holder | Workstation tables | 20 | 24"x10" |  | 4029 HON |  | OficeMart | 661.4 |  |  | 12540
CPU holder | - | 20 |  |  | CPU2 |  | OficeMart | 928.76 |  |  | 18100
Chairs | Stackable chairs | 20 | - |  | STC 3050 |  | OficeMart | 659.61 | 13192.2
Workstation for teacher |  | 1 | 48"x24"40" |  | - |  | GAYLOR | 13929.375 |  |  | 13929.375
High chair with wheels without armrests | Chair for teacher | 1 |  |  | B1690 |  | OficeMart | 898.07 | 898.07
Blackboard | Porcelain white board | 1 | 2.40 x 1.20 mts |  | - |  | Gusmar | 2903 |  |  |  |  | 2903
[8 empty] | TOTAL | 14090.27 |  | 91469.375 |  | 2903
Media Room
Table for teachers | Education Workstations | 3 | 48"x24"x29.5" |  | ED2448G HON |  | OficeMart | 2554.86 |  |  | 7692
Table for teachers | Education Workstations | 1 | 60"x24"x29.5" |  | ED2460G HON |  | OficeMart | 2752.96 |  |  | 2762
Table for teachers equipment | Education Workstations | 1 | 72"x24"x29.5" |  | ED2472G HON |  | OficeMart | 3176.49 |  |  | 3188
Contacts | Elect interlink 2 | 1 | - |  | ULSG2 |  | OficeMart | 3152.18
Contacts | Elect interlink 3 | 1 | - |  | ULSG3 |  | OficeMart | 4383.49
CPU holder | - | 4 | - |  | CPU2 |  | OficeMart | 928.76 |  |  | 3620
Keyboard holder | Workstations | 4 | 24"x10" |  | 4029 HON |  | OficeMart | 661.4 |  |  | 2508
Secretarial chair without armrests | Secretarial chair Vold 5700 | 4 |  |  | 5701GA HON |  | OficeMart | 1266.5 |  |  | 5200
[8 empty] | TOTAL | 0 |  | 24970
Audiovisual Resources
Screens (partitions) | lnitiate | 10 | 55"x24" |  | NP5524NCE HON |  | OficeMart | 1584.14 | 15841.4
Metallic panel structure | Initiate | 4 | 55"x42" |  | NR5542NCE |  | OficeMart | 2241.05 | 8964.2
Cover | lnitiate | 4 | 42"x24"x29.5" |  | NWR2442T |  | OficeMart | 1550.69 | 6202.76
Accessories | Initiate Varios | 1 | - |  | VARIOS |  | OficeMart | 4819.87 | 4819.87
Chairs | Stackable chairs | 4 | - |  | STC 3050 |  | OficeMart | 659.61 | 2638.44
[8 empty] | TOTAL | 38466.67
CRAI Reception
Cover | lnitiate | 1 | 48"X15" |  | NCS1548T HON |  | OficeMart | 21826.11 |  |  | 1720
Cover | lnitiate | 1 | 60"x15" |  | NCS1560T HON |  | OficeMart |  |  |  | 1814
Cover | lnitiate | 1 | 48"x24" |  | WR2448T HON |  | OficeMart | 1266.5 |  |  | 2103
Cover | lnitiate | 1 | 60"x24" |  | WR2460T HON |  | OficeMart | 928.76 |  |  | 2631
Screen | lnitiate | 1 | 60"x42" |  | NR4260F HON |  | OficeMart | 661.4 |  |  | 3549
Screen | lnitiate | 1 | 48"x42" |  | NR4248F HON | [5 empty] | 3144
Screen | lnitiate | 2 | 24"x42" |  | NR4224F HON |  | GAYLOR | 17887.5 |  |  | 4770
Reception accessories | Initiate Varios | 1 | - |  | - | [5 empty] | 2023
Secretarial chair without armrests | Secretarial chair Vold 5700 | 1 |  |  | 5701GA HON | [5 empty] | 1300
CPU holder |  | 1 | - | [7 empty] | 905
Keyboard Holder | For receptionist | 1 | 24"x10" |  | 4029 HON | [5 empty] | 627
Racks or shelves for DVD | Shelf back up | 4 | 34 1/2"x12 5/8"x71" |  | S72ABC |  | OficeMart | 10804.55 | 21609
Racks or shelves for 400 DVD | Desk shelf | 1 | 64"x40"x25" |  | GH-VS25236 | [5 empty] | 17887.5
[8 empty] | TOTAL | 21609 |  | 42473.5
Circulation Area
Secretarial chair without armrests | Secretarial Chair Vold 5700 | 3 | - |  | 5701GA HON |  | OficeMart | 1266.5 |  |  | 3900
[8 empty] | TOTAL |  |  | 3900
Consultation Area
Table | Query Table | 2 | 48"x24"40" |  | PT308439 VIRCO |  | OficeMart | 8775.41 |  |  |  | 12225
[8 empty] | TOTAL |  |  |  | 12225
Principal´s Office
Desk | Peninsular desk | 1 | 60"x30"x29.5" |  | 100-131 BOSAN |  | OficeMart | 1509.93 | 1509.93
Drawers and filing cabinet | Includes drawersand file | 1 | 42"x24"x29.5" |  | 100-197 BOSAN |  | OficeMart | 711.51 | 711.51
"Credenza" | "credenza" | 1 | 60"x24"x 29.5" |  | 100-117 BOSAN |  | OficeMart | 1505.58 | 1505.58
Fixed Pedestal | 2 drawers and one file cabinet | 1 | - |  | 100-166 BOSAN |  | OficeMart | 2035.29 | 2035.29
Bookcase on credenza |  | 1 | 60"x15"x36" |  | 100-141 BOSAN |  | OficeMart | 2334.5 | 2334.5
CPU holder | CPU holder | 1 | - |  | CPU2 |  | OficeMart | 928.76 | 928.76
Keyboard holder | Workshop station | 1 | 24"x10" |  | 4029 HON |  | OficeMart | 661.4 | 661.4
Chair | Semi -ejecutive chair | 1 | - |  | B8306 BOSS |  | OficeMart | 818.83 | 818.83
Chair | Chair for Visitors | 2 | - |  | STC 3050 |  | OficeMart | 659.61 | 1319.22
Metallic Bookcase | Metallic bookcase w/5 shelves. | 2 | 71"x34.5"x12" |  | S72ABC |  | OficeMart | 2611.11 | 5222.22
[8 empty] | TOTAL | 17047.24
Process Técnico
Escritorio | Shell type | 2 | 60"x30"x29.5" |  | 100-103 BOSAN |  | OficeMart | 1730.41 | 3460.82
Reversible Return |  | 2 | 24"x42"x29" |  | 100-196 BOSAN |  | OficeMart | 1006.39 | 2012.78
Pedestal | 2 drawers with lock | 2 | 19"x16"x22" |  | 100-107 |  | OficeMart | 1741 | 3482
Metallic File Cabinets | 4 drawers | 2 | 52"x18"x25" |  | 514CP HON |  |  | 3284.23 |  |  | 4392
Keyboard holder | worktables | 2 | 24"x10" |  | 4029 HON |  | OficeMart | 695.31 | 1390.62
CPU holder | - | 2 | - |  | CPU2 |  | OficeMart | 661.4 | 1322.8
Secretarial chair without armrest | Secretarial chair Vold 5700 | 4 |  |  | 5701GA HON |  | OficeMart | 1266.5 | 5066
Workstation table | CPU | 2 | 30"x60"x29.5" |  | UTM3060 HON |  | OficeMart | 2355.52 | 4711.04
Metallic Bookcase | 6 shelves | 8 | 34.5"x12 5/8"x81" |  | S82ABC'HON |  | OficeMart | 3475.83 | 27806.64
[8 empty] | TOTAL | 49252.7 |  | 4392
Periodicals
Metallic Bookcase | 6 shelves | 10 | 34.5"x12 5/8"x81" |  | S82ABC HON |  | OficeMart | 3580.11 | 35801.1
[8 empty] | TOTAL | 35801.1
Histórical Archive
Desk | Secretarial Chair Vold 5700 | 1 | 60"x30"x29.5" |  | 100-103 BOSAN |  | OficeMart | 1730.17 | 1730.17
Reversible return |  | 1 | 24"x42"x29" |  | 100-196 BOSAN |  | OficeMart | 1006.39 | 1006.39
Pedestal | With two drawers and lock | 1 | 19"x16"x22" |  | 100-107 |  | OficeMart | 1741 | 1741
Metallic File Cabinets | 4 drawers | 1 | 52"x18"x25" |  | 514CP HON |  | OficeMart | 3284.23 |  |  | 2196
Metallic Bookcase | 5 shelves | 2 | 34.5"x12"x71" |  | S72ABC |  | OficeMart | 2611.11 | 5222.22
Keyboard holder | Workshop tables | 1 | 24"x10" |  | 4029 HON |  | OficeMart | 661.4 | 661.4
CPU holder | CPU holder | 1 | - |  | CPU2 |  | OficeMart | 928.76 | 928.76
Secretarial chair withour armrest | Secretarial Chair Vold 5700 | 1 |  |  | 5701GA HON |  | OficeMart | 1266.5 | 1266.5
[8 empty] | TOTAL | 12556.44 |  | 2196
Área for Staff
Folding Table |  | 1 | 72"x18"x 29.5" |  | 611872 VIRCO |  | OficeMart | 3247.08 | [6 empty] | 3247.08
Metallic Lockers | with 4 divisions | 2 | 12"x12"x72" |  | L3109 |  | OficeMart | 1309.88 | 2619.76
Chairs | Stackable chairs | 2 | - |  | STC 3050 |  | OficeMart | 659.61 | 1319.22
[8 empty] | TOTAL | 3938.98 | [5 empty] | 3247.08
Copy Area
Metallic Cabinet | for 5 sections with doors | 1 | 36"x18"x72" |  | SC1872 |  | OficeMart | 4933.75 |  |  | 4962
[8 empty] | TOTAL |  |  | 4962
Consultation Island (heritage area)
Table | Table for consultation | 1 | 24"x"24"x40 |  |  |  | GAYLOR | 7492.5 |  |  |  | 7275
[8 empty] | TOTAL |  |  |  | 7275
Group Work Table
Table | Table for 4 persons | 3 |  |  |  |  | Gensa | 7627.5 |  |  |  | 14025
Chair | Stackable chair | 8 | - |  | STC 3050 |  | OficeMart | 659.61 | 5276.88
[8 empty] | TOTAL | 5276.88 |  |  | 14025
Cubicle Tables
Rectangular table | for 6 persons | 6 | 0.80cm.x1.81cm. |  | - |  | Gensa | 7627.5 |  |  |  | 31500
Boat type table | for 10 persons | 1 | 1.22cm.x3.05mts. |  | - |  | Gensa | 8302.5 |  |  |  | 12975
[8 empty] | TOTAL |  |  |  | 44475
Cultural Heritage
Book Shelves | Double side | 15 | 2.20mt x 1.01mt x 80cm |  | - |  | Comander | 8530 | [5 empty] | 127950
Book shelves | Single side | 10 |  |  | - |  | Comander | 4680 | [5 empty] | 46800
[8 empty] | TOTAL |  | 0 |  |  |  | 174750
Magazines Area
Magazines Rack | Shelf for magazines | 2 |  |  |  |  | GAYLOR | 6601.5
Newspaper Rack | Individual table for student | 1 |  |  |  |  | GAYLOR | 7087.5 |  |  |  | 4000
[8 empty] | TOTAL |  | 0 |  | 4000
[9 empty] | 219840 | 0 | 255217.25 | 90907.75 | 5518 | 174750 | 3247.08
[8 empty] | IVA | 24182.4 | 0 | 28073.8975 | 9999.8525 | 606.98 | 19222.5 | 357.1788
[8 empty] | TOTAL | 244022.4 | 0 | 283291.1475 | 100907.6025 | 6124.98 | 193972.5 | 3604.2588
[11 empty] | 749480.08 | TOTAL
[11 empty] | 82442.8088 | VAT
[11 empty] | 831922.8888 | TOTAL IN PESOS
66553.8311
TOTAL IN DLLS.

## EQUIPO
CENTRO DE ENSEÑANZA TÉCNICA Y SUPERIOR
Departament of Computing and Telecommunications
Proposal Infrastructure of Computing Equipment and Technologies of Information
Center of Resources for Learning and Investigation (CRAI )
Unit/Article | Description /Application | Quantity | Costo 2009 | Costo Total 2009 | Cost 2010 | Total Cost 2010
Electronic Room
Computing Equipment | Core 2 Duo E8400, 2GB Mem, 160 GB HD, LCD 17" | 20 | 584 | 11680 | 835 | 16700
Instruction equipment | Laptop Vostro 1014 Core 2 Duo T6570, 2GB Mem, 160GB HD, 14" | 1 |  |  | 725 | 725
Printer LaserJet |  | 1 | 350 | 350 | 350 | 350
Projection | Projector, Electric screen, speakers, connectors, driver | 1 |  |  | 4502.54 | 4502.54
Installation | Installations, configurations and accessories | 1 |  |  | 815.38 | 815.38
Training Room
Instruction equipment | Laptop Vostro 1014 Core 2 Duo T6570, 2GB Mem, 160 GB HD, 14" | 1 |  |  | 725 | 725
Projection | Projector, Electric screen, speakers, connectors, driver | 1 | 3632.01 | 3632.01 | 4502.54 | 4502.54
Installation | Installations, configurations and accessories | 1 | 411.28 | 411.28 | 815.38 | 815.38
Media Room
Equipment | Core 2 Quad 9400, 4GB Mem, 250GB HD, LCD 19", Video 1GB | 4 | 850 | 3400 | 1035 | 4140
Scaner |  | 1 | 200 | 200 | 198 | 198
Digital Camara |  | 1 | 800 | 800 | 805 | 805
Tripod |  | 1 |  |  | 35 | 35
Impresora LaserJet Color |  | 1 | 500 | 500 | 515 | 515
Design tablet |  | 4 | 270 | 1080 | 185 | 740
Counter CRAI
Computer |  | 1 |  |  | 690 | 690
Printer Laser |  | 1 |  |  | 165 | 165
Audiovisual Resources
Playback stations | Dell Vostro 320 - All-in-One; Sony Studio Headphone | 4 |  |  | 948 | 3792
Chamber of Documents | High quality presentations and definition SDP850/DX | 1 |  |  | 1297 | 1297
Video Camara | Videoconferencing Camara | 1 |  |  | 820 | 820
Microphone & base |  | 1 |  |  | 590 | 590
Lapel microphone |  | 1 |  |  | 550 | 550
Lector Blue-Ray | Video Playback | 1 |  |  | 200 | 200
Video Production | TriCaster All in one | 1 |  |  | 8000 | 8000
| S u b - T O T A L |  |  | 22053.29 |  | 51672.84
Video Room
Unit/Article | Description /Application | Quantity | Costo 2009 | Costo Total 2009 | Cost 2010 | Total Cost 2010
Video Room | Projector, Manual screen, connectors | 2 | 1900 | 3800 | 1900 | 3800
| S u b - T O T A L |  |  | 3800 |  | 3800
Communications Infrastructure (voice and data)
Unit/Article | Description /Application | Quantity | Costo 2009 | Costo Total 2009 | Cost 2010 | Total Cost 2010
Wring UTP | Wring UTP Cat 5E brand Panduit. | 10 | 135.49 | 1354.9 | 135.49 | 1354.9
Wring UTP | Wring UTP Cat 5E brand Panduit. | 3 |  | 0 | 135.49 | 406.47
Communication Cabinet | Rack, vertical & horizontal, organizers patch panel modular. | 1 | 883.21 | 883.21 | 883.21 | 883.21
Channeling | gangway, fast connections, threaded rod, securing clips, profile, accessories. | 1 | 1049.54 | 1049.54 | 1049.54 | 1049.54
Connectivity in workstations. | Face plates, plugs, jacks, patch cord. | 1 | 1122.89 | 1122.89 | 1122.89 | 1122.89
Wireless network | Access point | 1 | 490 | 490 | 880 | 880
Miscellaneous | Bolts, cutting disk, drill, etc. | 1 | 100 | 100 | 100 | 100
Miscellaneous | S u b - T O T A L |  |  | 5000.54 |  | 5797.01
Sefety
Unit/Article | Description /Application | Quantity | Costo 2009 | Costo Total 2009 | Cost 2010 | Total Cost 2010
Seguridad para libros | Antenas de seguridad para libros | 3 | 8000 | 24000 |  | 0
Security for Books | Security antennas for books | 1 | 5580 | 5580 | 5580 | 5580
Closed circuit | S u b - T O T A L |  |  | 29580 |  | 5580
|  | T O T A L |  | 60433.83 |  | 66849.85
|  | VAT |  | 6043.383 |  | 7353.4835
|  | TOTAL |  | 66477.213 |  | 74203.3335
CENTRO DE ENSEÑANZA TÉCNICA Y SUPERIOR
Department of Computing and Telecommunications
Proposal Infrastructure of Computing Equipment and Technologies of Information
Phase 1
Unit/Artcle | Description /Application | Quantity | Costo 2009 | Costo Total 2009 | Cost 2010 | Total Cost 2010
Wring UTP | Wring UTP Cat 5E brand Panduit. | 7 | 135.49 | 948.43 | 135.49 | 948.43
Communication Cabinet | Rack, vertical & horizontal organizers, patch panel modular. | 1 | 883.21 | 883.21 | 883.21 | 883.21
Channeling | Gangway, fast connections, threaded rod, safety clips, profile, accessories. | 1 | 1049.54 | 1049.54 | 1049.54 | 1049.54
Connectivity | Face plates, plugs, jacks, patch cord. | 1 | 622.89 | 622.89 | 622.89 | 622.89
Miscellaneous | Bolts, cutting disk, drill, etc. | 1 | 100 | 100 | 100 | 100
Video Rooms | Projector, manual screen, connectors | 2 | 1900 | 3800 | 1900 | 3800
| S u b - T O T A L |  |  | 7404.07 |  | 7404.07
Phase 2
Unit/Article | Description /Application | Quantity | Costo 2009 | Costo Total 2009 | Cost 2010 | Total Cost 2010
Center of Resources for Learning and Research (CRAI )
Electronic Room
Computing equipment | Core 2 Duo E8400, 2GB Mem, 160 GB HD, LCD 17" | 20 | 584 | 11680 | 835 | 16700
Instruction equipment | Laptop Vostro 1014 Core 2 Duo T6570, 2GB Mem, 160GB HD, 14" | 1 |  |  | 725 | 725
Printer LaserJet |  | 1 | 350 | 350 | 350 | 350
Projection | Projector, Electric screen, speakers, connectors, driver | 1 |  |  | 4502.54 | 4502.54
Installation | Installations, configurations and accessories | 1 |  |  | 815.38 | 815.38
Training Room
Instruction equipment | Laptop Vostro 1014 Core 2 Duo T6570, 2GB Mem, 160 GB HD, 14" | 1 |  |  | 725 | 725
Projection | Projector, Electric screen, speakers, connectors, driver | 1 | 3632.01 | 3632.01 | 4502.54 | 4502.54
Installation | Installations, configurations and accessories | 1 | 411.28 | 411.28 | 815.38 | 815.38
Media Room
Equipment | Core 2 Quad 9400, 4GB Mem, 250GB HD, LCD 19", Video 1GB | 4 | 850 | 3400 | 1035 | 4140
Scaner |  | 1 | 200 | 200 | 198 | 198
Digital Camara |  | 1 | 800 | 800 | 805 | 805
Tripod |  | 1 |  |  | 35 | 35
Printer LaserJet Color |  | 1 | 500 | 500 | 515 | 515
Design Tablets |  | 4 | 270 | 1080 | 185 | 740
Counter CRAI
Computer |  | 1 |  |  | 690 | 690
Printer Laser |  | 1 |  |  | 165 | 165
Audiovisual Resources
Playback stations | Dell Vostro 320 - All-in-One; Sony Studio Headphone | 4 |  |  | 948 | 3792
Chamber of Documents | High quality presentations & definition SDP850/DX | 1 |  |  | 1297 | 1297
Video Camara | Videoconferencing camara | 1 |  |  | 820 | 820
Microphone and base |  | 1 |  |  | 590 | 590
Lapel microphone |  | 1 |  |  | 550 | 550
Lector Blue-Ray | Videos playback | 1 |  |  | 200 | 200
Video playback | TriCaster All in one | 1 |  |  | 8000 | 8000
Infrastructure of communications (voice and data)
Wring UTP | Wring UTP Cat 5E brand Panduit. | 3 | 135.49 | 406.47 | 135.49 | 406.47
Wring UTP | Wiring UTP Cat 5E brand Panduit. (Additional for changes) | 3 |  |  | 135.49 | 406.47
Connectivity | Face plates, plugs, jacks, patch cord. | 1 | 500 | 500 | 500 | 500
Wireless network | Access Point | 1 | 490 | 490 | 880 | 880
Security
Security for books | Security Antennas for books | 3 | 8000 | 24000
Closed Circuit | Closed Circuit System | 1 | 5580 | 5580 | 5580 | 5580
| S u b - T O T A L |  |  | 53029.76 |  | 59445.78
|  | T O T A L |  | 60433.83 |  | 66849.85
|  | I V A |  | 6043.383 |  | 7353.4835
|  | T O T A L |  | 66477.213 |  | 74203.3335
Comments:
- It was considered for this proposal for computers, to continue with the standard of laboratories of the campus which have equipment brand DELL or IBM.
- The increase in the price of the equipment of the Media Room and Electronic Room is because in the 2009-2, budget, it was quoted equipment unbranded,
which only has one year guarante in parts not including any type of service, besides the lifetime estimated is 3 years.
- This proposal is for equipment brand DELL, which has 3 years warranty in parts and service and a lifetime estimated of 4 to 5 years,
besides this equipment is more updated.
- The difference in price of other equipment to this proposal is not considerable.

## Concentrado totales dlls
Concentrate costos of remodeling library
Civil Work | 119560.5956
Furniture | 66553.8311
Computing Equipment | 74203.3335
Contingencies for civil work 5% | 5978.0298
266295.79
Prices in dollars include VAT, subject to change for starting time of works and modifications to project
It is considered a contingeny entry in civil works of 5% of total construction works, according to the experience in remodeling works which show details not considered in the project.

## Gasto Real
12.5
| REAL |  |  |  | Presupuestado
| Expenditure | VAT | Total |  | Monto con IVA | Diferencia | Comments | PRESUPUESTADO | DIFERENCIA
Civil Work |  |  |  | 159509.9251 |  |  |  | 119560.5956 | -39949.3295
Arq. Elio | 1389224.42 | 152814.6862 | 1542039.1062 | 123363.1285 | 1162236.2819 | -379802.8243 | Extra work primarily baseboard, demolition and exterior work
GENSA | 222819.87 | 24510.1857 | 247330.0557 | 19786.4045 | 232239.75 | -15090.3057 | Removal of existent ductwork & exhaust or extractors out of service in consultation area
Victorino Justino | 184238.65 | 20266.2515 | 204504.9015 | 16360.3921 | 100031.4129 | -104473.4886 | Carpet in area of knowledge
|  |  | 1993874.0634 | 159509.9251 | 1494507.4448 | -499366.6186
Mobiliario |  |  |  | 70534.054 |  |  |  | 66553.8311 | -3980.2229
Oficemart | 185790.61 | 20436.9671 | 206227.5771 | 16498.2062 | 244022.4 | 37794.8229
JFA | 228698 | 25156.78 | 253854.78 | 20308.3824 | 283291.1475 | 29436.3675
Comander | 220810 | 24289.1 | 245099.1 | 19607.928 | 193972.5 | -51126.6 | Chairs that were removed to Officemart and bought to Comander
GUSMAR | 5230 | 575.3 | 5805.3 | 464.424 | 6124.98 | 319.68
GENSA | 153773.8 | 16915.118 | 170688.918 | 13655.1134 | 100907.6025 | -69781.3155 | Maintenance to furniture, tables and carpentry that was not covered.
J Flores | 0 | 0 | 0 |  | 3604.2588 | 3604.2588
|  |  | 881675.6751 | 70534.054 | 828318.63 | -53357.0451
CCTV |  |  |  | 4877.34 |  |  |  | 5580 | 702.66
APSyC | 54925 | 6041.75 | 60966.75 | 60966.75 | 77422.5 | 16455.75
|  |  | 60966.75 | 60966.75 | 77422.5 | 16455.75
CONTINGENCY EXPENSE | [7 empty] | 5978.0298 | 5978.0298
[5 empty] | 74725.3722 | 74725.3722
[8 empty] | TOTAL DIFERENCIA | -37248.8626 | dlls Inc. IVA
|  | Total investment | 2936516.4885 |  | Gran total | -461542.5415
Note on B15: jorge.garcia: muebles de madera, mesas de cubiculos, mantenimento a recepcion
Note on B6: jorge.garcia: A/C, contactos en area de mezanine, conexion de mesas de sala electronica